## Sheet1
SCHEDULE OF PLANNING CONDITIONS |  | general compliance | For internal team use only
PROJECT NAME: Iceland Site, Wood Green, Haringey |  | prior to commencement of above ground works
PLANNING APP REF: HGY/2017/2886 |  | prior to commencement of development
LAST UPDATE: 03/03/23 |  | condition specific trigger point
pre occupation
Condition No | Description | Type | Status | Action | Application | Date Submitted | Date Discharged/approved | Relevant email/documents
1 | Time limit. The development hereby authorised must be begun not later than the expiration of 2 years from the date of this permission, failing which the permission shall be of no effect. | General compliance (time limited) | Other conditions in permission require discharging prior to commencement of development on site.
2 | Approved drawings. The development hereby authorised shall be carried out in accordance with the following approved plans and specifications: WGR-CAA-XX-XX-DR-A-0100/P1; 0101/P1; 0102/P1; 1001/P3; 1002/P3; P1003/P2; 2000/P4; 2001/P4; 2002/P4; 2003/P5; 2004/P4; 2006/P2; 2010/P4; 2011/P3; 2012/P3; 2020/P3; 3001/P3; 3002/P3; 3003/P4; 3004/P4; 3005/P4; 3006/P4; Email received from Bryony P Jennings on 12/03/2018 (Affordable Mix & Location); and, 8688-BOW-A1-01-DR-A-0001-P3 (Proposed Phasing Strategy) | General compliance. | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022)
3 | Materials to be approved. Prior to the commencement of above ground works to any phase of the development hereby approved details of appropriately high quality and durable finishing materials to be used for the external surfaces of that phase of development, including samples shall be submitted to and approved in writing by the Local Planning Authority. Samples shall include example external panelling at a minimum, combined with a schedule of the exact product references for other materials. | Prior to commencement of above ground works | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022). Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase.
4 | Cycle parking design. Prior to the commencement of above ground development of any phase of development hereby approved details of the provision and design of cycle parking for that phase shall be submitted to and approved by the Local Authority be at the very least in accordance with the 2016 London Plan and London Cycle Design Standard and accredited to a minimum of PAS24:2016 accreditation, with self closing, self-locking mechanism, fob access into the store and push button to release to exit and as far as practicable provision shall be in accordance with the Publication London Plan 2020 | Prior to the commencement of above ground development. | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022)
5 | Electric charging facilities. Prior to the first occupation of the development hereby approved a provision of 20% of the total number of car parking spaces shallhave active electric charging points, with a further passive provision for conversion of all parking spaces to be equipped with electric charging points and such provision shall be retained thereafter unless otherwise agreed in writing. | Pre occupation
6 | Delivery, service and waste management. Prior to the first occupation of the development ereby approved, a Delivery and Servicing Plan (DSP) shall be submitted to and approved by the Local Planning Authority. Such DSP shall include a waste management plan which includes details of how refuse is to be collected from the site and secure bin store areas and shall be prepared in line with the requirements of the Council's waste management service which must ensure that all bins are within 10 metres carrying distances of a refuse truck on a waste collection day. | Pre occupation
7 | Refuse storage. Prior to the first occupation of the residential and commercial units hereby approved details of separate refuse storage facilities shall be submitted to and approved by the Local Planning Authority in shall be accredited to a minimum of PAS24:2016, be self closing, self locking with two Maglock minimum. Access and exit should be via fob only from the core of the building with push button or thumb turn release into the public highway. | Pre occupation
8 | Gated access to the car park . Prior to first occupation of the development hereby approved details of the entrance to the undercroft car parking facility shall be submitted to and approved in writing by the Local Planning Authority and shall be retained as such in perpetuity unless otherwise agreed in writing. Any gates shall be accredited to LPS 1175 SR2 and to be fob access entry and exit only. | Pre occupation
9 | Design code for public realm. Prior to commencement of above ground works of the relevant phase of development (save for demolition) hereby approved a detailed design code for the public realm areas of and surrounding the site, shall be submitted to and approved in writing by the Local Planning Authority. Public realm works shall be undertaken in accordance with this design code and shall be retained as such thereafter, unless otherwise agreed in writing. | Prior to commencement of above ground works | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022). Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase.
10 | Piling Method Statement. No piling shall take place until a piling method statement (detailing the depth and type of piling to be undertaken and the methodology by which such piling will be carried out, including measures to prevent and minimise the potential for damage to subsurface sewerage infrastructure, and the programme for the works) has been submitted to and approved in writing by the local planning authority in consultation with Thames Water. Any piling must be undertaken in accordance with the terms of the approved piling method statement. | Prior to piling commencing | Condition requires approval of details relevant to boreholes / piling before such activities take place (as opposed to purely being prior to commencement of development in general). This query was put to John McRory in email dated 13.12.22. | Condition requires a piling method statement for prior approval
11 | Crossrail 2 safeguarding. The relevant phase of the development hereby permitted shall not be commenced (save for demolition) until detailed design and Construction method statements for all of the ground floor structures, foundations and basements and for any other structures below ground level, including piling and any other temporary or permanent installations and for ground investigations have been submitted to and approved in writing by the Local Planning Authority. | Prior to commencement (excluding demolition) | Details for partial approval submitted (Phase 1 only). Case Officer indicated (email dated 06.12.22) that condition drafted up for sign off. |  | Submission no. HGY/2022/2610 | 2022-09-06 |  | Email from Case Officer (CO) dated 06.12.22 stating: "I have drafted up conditions 11 (CR) 14 (site levels) and 20 (air quality). I can pass these through this week with an agreed Extension of Time for 09/12/2022." Email to CO (07.10.22) attaching email from Crossrail 2 Safeguarding Manager (dated 13.09.22) confirming: "Given the distance of the distance between the phase 1 building and the proposed Crossrail 2 running tunnels and the fact that the analysis considered the worst case scenario I am minded to accept the report’s conclusions. Am I right in thinking that you will now submit these reports to the local planning authority to discharge the condition in relation to phase 1? If this is the case it would be a swift turn-around for us to respond to the Council with our advice. "
12 | External Lighting. Prior to first occupation of the development hereby approved details of all permanent external lighting to building facades, street furniture and public realm features, including the relevant elements of the wind mitigation strategy, to comply with British Standard 5489:2003, utilizing dusk till dawn photo electrical cell lighting with manual override, shall be submitted to and approved in writing by the Local Planning Authority. The agreed lighting scheme shall be retained as such thereafter. | Pre occupation
13 | Business and Community Liaison construction Group. For the duration of the construction phase of development the Applicant will establish and maintain a Liaison Group. <further details of scope in full condition wording>. The terms of reference for the Liaison Group should be submitted to the Council for approval prior to commencement of the development. The Liaison Group will meet at least once every month with the first meeting taking place one month prior to the commencement of development and the meetings shall become bimonthly after the expiry of a period of four (4) months thereafter or at such longer period as the Liaison Group shall agree. | Prior to the commencement of development with first meeting one month prior | >Further details provided to case officer e.g. invites to be issued ot residents association. > Awaiting response from Case Officer on acceptability of proposed changes to Terms of Reference Document. | Terms of reference submitted for approval, first meeting required to be held one month prior to works commencing. | Submission no. HGY/2022/2611 | 2022-09-06 |  | Email to CO (31.01.23) submitted updated Terms of Refernce document following a request. This does not appear to have been uploaded to Public Access. The submission follows an ealier version sent to the CO whereby he subsequently confirm (email 30.01.23 further down the same email chain) that the report "seems okay on the face of it" and he would write it up for review by management at the end of the following week.
14 | Confirmation of site levels. Prior to the commencement of the relevant phase of development (except demolition works) details of all existing and proposed levels on the site in relation to the adjoining properties be submitted to and approved by the Local Planning Authority. | Prior to commencement (excluding demolition works) | Site level details submitted. Case Officer indicated (email dated 06.12.22) that condition drafted up for sign off. |  | Submission no. HGY/2022/2612 | 2022-09-06 | 2023-01-13
15 | Contamination (1). Using the information from the CGL contamination report a site investigation shall be designed for the site. This shall be submitted to, and approved in writing by the Local Planning Authority prior to that investigation being carried out on the site. The investigation must be comprehensive enough to enable:- 1. a risk assessment to be undertaken, 2. refinement of the Conceptual Model, and 3. the development of a Method Statement detailing the remediation requirements. The risk assessment and refined Conceptual Model shall be submitted, along with the site investigation report, to the Local Planning Authority. B) If the updated risk assessment and refined Conceptual Model indicate any risk of harm, a Method Statement detailing the remediation requirements, using the information obtained from the site investigation and the potential effects set out in the Environmental Statement dated December 2016, and also detailing any post remedial monitoring shall be submitted to, and approved in writing by, the Local Planning Authority prior to that remediation being carried out on site. | Approval required prior to site investigation and/or remediation work (relates to conditions 42 and 44) | >Details for partial approval submitted (Phase 1 only). > Lead Officer (Pollution) responded on 11.01.23 to confirm Condition 15(a) and 42(1)and(2) can be discharged. Noted this ONLY relates to Phase 1 and no work on others phases should take place prior to further details being agreed. The Officer seeks a remediation strategy and verification plan prior to discharging other element of conditions. > 15(b) (the remaining part of the condition) requires a Method Statement to be agreed by the LPA prior to that remediation being carried out. > 42(3)and(4) (the remaining part of the condition) - it is not clear if these are considered as needing to be agreed prior to development although 42(3) requires remediation based on the Site Investigation Report which, itself simply recommends certain measures to be observed during groundworks to mitigate impacts of asbestos contamination. 42(4) requires a verification plan which presumably cannot be completed until the remediation works are complete. |  | Submission no. HGY/2022/2615 | 2022-09-06 |  | Latest response from EHO dated 21.02.23 confirming "we are satisfied with the further discharge of condition 15B (Remediation Method Statement) and 42 (3) (Remediation strategy giving full details of the remediation measures) for ONLY the Phase 1 of the approved planning permission HGY/2017/2886." Response from EHO 11.01.23 - we are satisfied with the partial discharge of ONLY condition 15 (A) on the (site contamination risk assessment and investigation) and 42 (1) and (2) (Additional Contamination - risk assessment and investigation) for the Phase 1 of the approved planning permission HGY/2017/2886.
16 | Contamination (2). Where remediation of contamination on the site is required completion of the remediation detailed in the method statement shall be carried out and a report that provides verification that the required works have been carried out, shall be submitted to, and approved in writing by the Local Planning Authority before the development is occupied. | Pre occupation |  | This condition is only triggered in the event of contamination on the site is identified.
17 | Mobile Machinery. No works shall commence on the site until all plant and machinery to be used at the demolition and construction phases meets Stage IIIA of EU Directive 97/68/ EC for both NOx and PM and all Non-Road Mobile Machinery (NRMM) and plant to be used on the site of net power between 37kW and 560 kW has been registered at http://nrmm.london/. Proof of registration must be submitted to the Local Planning Authority prior to the commencement of any works on site. | Prior to commencement of any works | Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase. | Proof of registration required to be provided to the LPA - no approval needed | Submission no. HGY/2022/2613 | 2022-09-06 | 16.02.23
18 | Mobile machinery inventory. An inventory of all NRMM must be kept on site during the course of the demolitions, site preparation and construction phases. All machinery should be regularly serviced and service logs kept on site for inspection. Records should be kept on site which details proof of emission limits for all equipment. This documentation should be made available to local authority officers as required until development completion. | General compliance. |  | Condition requires a log of all NRMM to be kept on site and made readily available to the Council if required.
19 | Additional AQ assessment (energy centre detail). Prior to above ground works, a revised Air Quality assessment including predicted concentrations incorporating combustion plant emissions and an AQ neutral assessment with a comparison of development emissions against London Plan emission benchmarks for buildings. Details shall include and relate to transportation details and confirm that the emissions from this single Energy Centre are managed, which shall be mitigated in line with the GLA Air Quality SPG and shall include flue dispersal models, and emissions management on the pollutants. | Prior to commencement of above ground works
20 | Air quality (Dust). Prior to the commencement of the relevant phase of development hereby approved, an Air Quality and Dust Management Plan (AQDMP), detailing the management of demolition and construction dust, shall be submitted in writing to and for approval by the Local Planning Authority. The (AQDMP) shall be in accordance with the GLA SPG Dust and Emissions Control and include an updated Dust Risk Assessment in substantial accordance with the Dust Risk Assessment dated December 2016. The plan shall be implemented as approved and maintained for the duration of the construction phase of the development. | Prior to commencement of relevant phasse of development. | AQDMP submitted for approval. Case Officer indicated (email dated 06.12.22) that condition drafted up for sign off. |  | Submission no. HGY/2022/2614 | 2022-09-06 | 2023-01-13
21 | Secured by design certification. Part A - Prior to carrying out above grade works of each building or part of any new building, details shall be submitted to and approved, in writing, by the Local Planning Authority to demonstrate that such building or such parts of a building can achieve full Secured by Design' Accreditation. The development shall only be carried out in accordance with the approved details. Part B - Prior to the first occupation of each building or part of a building or use, a 'Secured by Design' accreditation shall be obtained for such building or part of such building or use. | Part A -Prior to commencement of any above grade works. Part B - pre occupation
22 | Secure lobby detailing. Prior to the first occupation of the development hereby approved, details for the communal entrance lobby and access system, including key fob entry system and internal mailboxes for each apartment shall be submitted to and approved by the Local Planning Authority and shall be retained as such unless otherwise approved in writing. | Pre occupation
23 | CCTV installation. CCTV systems shall be installed to BS EN 50132-7:2012 CCTV surveillance systems for use in security applications. The design of a CCTV system should be co-ordinated with the existing or planned lighting system for the buildings and the external grounds, to ensure that the quality of the lighting is sufficient to support the CCTV. Remotely monitored detector activated CCTV systems must be installed in accordance with BS 8418:2010 Installation and remote monitoring of detector operated CCTV systems - Code of practice. | General compliance. |  | Council to be notified of installation but no details required for approval.
24 | Confirmation of achieving energy efficiency standards and carbon reduction targets. The development shall be in accordance with the efficiency standards as set out in the Energy Strategy, by Project 23, Revision P1, dated July 2017 and shall achieve BREEAM Excellent and Home Quality Mark 3 Stars and maintained as such thereafter. A post construction certificate shall then be issued by an independent certification body, confirming this standard has been achieved. This must be submitted to the local authority at least 6 months of completion on site for approval. In the event that the development fails to achieve the agreed rating for the whole development, a full schedule and costings of remedial works required to achieve this rating shall be submitted and approved by the Local Planning Authority within 2 months of the submission of the post construction certificate. Thereafter the schedule of remedial works must be implemented on site within 3 months of the local authority's approval of the schedule, or the full costs and management fees given to the Council for offsite remedial actions. | post-construction certificate required for approval 6 months from completion on site |  |  |  |  | 3
25 | Roof top PV panels. Prior to the occupation of the development for residential purposes, details of the layout and specification of the PV solar panel installation for each individual building hereby approved shall be submitted in writing to and approved by the Local Planning Authority. The installation shall be constructed in accordance with the approved details and maintained thereafter. | Pre occupation (for residential purposes)
26 | Overheating. Prior to commencement of above ground works of the relevant phase of development (save for demolition), minimal risk of overheating shall be insured through the compilation of results of dynamic thermal modelling (under London's future temperature projections) for all internal spaces shall be submitted to and approved by the Local Planning Authority and shall be operational prior to the first occupation of the development hereby approved | Prior to commencement of above ground works | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022) | dynamic thermal modelling results required for approval by the Council prior to relevant development phase
27 | Boilers. Prior to installation, details of the Ultra Low NOx boilers for space heating and hot water should be forwarded to the Local Planning Authority. The boilers to be provided for space heating and domestic hot water shall have dry NOx emissions not exceeding 40 mg/kWh. | Prior to boiler installation |  | boiler details required to be supplied to the Council - no approval required
28 | Tree replacement. Prior to the first occupation of the development hereby approved, details of the proposed native species of replacement tress shall be submitted to and approved by the Local Planning Authority and shall be planted in accordance with the tree planting plans hereby approved. Any tree or plant on the development (including roof top amenity areas) which, within a period of five years of occupation of the approved development 1) dies 2) is removed 3) becomes damaged or 4) becomes diseased, shall be replaced in the next planting season with a similar size and species of tree or plant. | Pre occupation |  | tree planting details required for approval
29 | Sustainable drainage. Prior to the commencement of above ground works details of the design, implementation, maintenance and management of the sustainable drainage scheme shall be submitted to, and approved in writing by, the local planning authority. | prior to commencement of above ground works | Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase. | SUDs details required for approval prior to above ground works
30 | Hard and soft landscaping. Prior to the commencement of above ground works, full details of both hard and soft landscape works for the public realm areas, roof garden, podium garden, undercroft parking shall be submitted to and approved in writing by the Local Planning Authority and these works shall thereafter be carried out as approved. | prior to commencement of above ground works | Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase.
31 | Configuration of child playspace. Prior to the first occupation of the development hereby approved, a plan for the location of accessible playspace and calculation of projected children within the development shall be submitted to and approved by the Local Planning Authority. Such a plan shall provide sufficient amount of playspace and suitable play equipment for the projected number of children on site | Prior to first occupation
32 | Accessible dwellings. All the residential units will be built to Part M(2) 'accessible and adaptable dwellings' of the Building Regulations 2010 (as amended) and at least 10% shall be wheelchair accessible or easily adaptable for wheelchair use in accordance with Part M4(3) of the same Regulations, unless otherwise agreed in writing with the Local Planning authority. | General compliance.
33 | Internal noise levels within residential. The completion of the residential units shall be in accordance with the Environmental Noise Assessment (6415727/4 – July 2017), with the installation of appropriate double glazed insulating units together with the provision of forced ventilation, the internal noise levels within the proposed residential units (with the windows closed) will be in accordance with BS8233:2014. A test shall be carried out prior to the discharge of this condition to show that the required noise levels have been met and the results submitted to the Local Planning Authority for approval. | At completion of residential units. |  | internal noise test results required to be submitted to LPA for approval
34 | Sound installation. Prior to the commencement of above ground works of the relevant phase of development (save for demolition), details of a sound insulation scheme to be installed between the commercial premises on the ground floor and residential premises on the first floor shall be submitted in writing to and for approval by the Local Planning Authority. The scheme shall be submitted following consultation with the Environmental Health Officer. The scheme shall be installed as approved prior to any commercial occupation of the site and shall be maintained thereafter. | prior to commencement of above ground works | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022)
35 | Plant noise limits. Noise arising from the use of any plant and or associated equipment shall not increase the existing background noise level (LA90 15mins) when measured (LAeq 15mins) 1 metre external from the nearest residential or noise sensitive premises. The applicant shall also ensure that vibration/structure borne noise derived from the use of any plant equipment does not cause noise nuisance within residential or noise sensitive premises. | General compliance.
36 | Central dish/ receiving system. Prior to the occupation of the development, details of a Central Satellite Dish / Receiving System for the residential units hereby approved shall be submitted in writing to and for approval by the Local Planning Authority. The System shall be implemented in accordance with approved details and maintained thereafter and the placement of any Additional satellite dish or television antenna on any external surface of the development is precluded. | Prior to occupation.
37 | Obscure glazing in SW elevation. Before the first occupation of the development hereby permitted, the residential windows in the southwestern elevation shall be fitted with obscured glazing and any part of the window that is less than 1.7 metres above the floor of the room in which it is installed shall be non-opening and fixed shut. The windows shall be permanently retained in that condition thereafter. | Prior to occupation.
38 | Amended roof access design for 4th Core. Notwithstanding the information on the drawings hereby approved, a detailed drawing depicting the design, scale, massing of the access to the 4th Core roof area shall be submitted to and approved by the Local Planning Authority and such access shall be implemented in accordance with such drawings and retained as such unless otherwise agreed in writing. | Revised roof design required prior to its implementation.
39 | Comprehensive shopfront detail. Prior to the first occupation of the flexible retail units and medical centre hereby approved a scheme for the provision of a coherent and high quality fascia design for future signage, awnings and frontage details shall be submitted to and approved in writing by the Local Planning Authority and shall be retained as such unless otherwise approved in writing. | Prior to occupation (retail units and medical centre)
40 | No A5 retail use. Notwithstanding the information on the drawings hereby approved, no use of the flexible retail units hereby approved shall be used as hot food takeaway (A5) use unless otherwise agreed in writing by the Local Planning Authority. | General compliance.
41 | Revised parking layout. Notwithstanding the approved plans, a revised parking layout demonstrating how access for maintenance / works to the Moselle River will be maintained, shall be submitted to and approved in writing by the Local Planning Authority prior to the commencement of above ground works of the relevant phase of development. The development shall thereafter be built only in accordance with the approved. | prior to commencement of above ground works | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022). Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase.
42 | Contamination remediation. Prior to each phase of development approved by this planning permission no development (save for demolition) shall commence until a remediation strategy to deal with the risks associated with contamination of the site has been submitted to, and approved in writing by, the Local Planning Authority. <further details in full condition>. | Prior to commencement of each phase of development (excluding demolition) | >Details for partial approval submitted (Phase 1 only). > Lead Officer (Pollution) responded on 11.01.23 to confirm Condition 15(a) and 42(1)and(2) can be discharged. Noted this ONLY relates to Phase 1 and no work on others phases should take place prior to further details being agreed. The Officer seeks a remediation strategy and verification plan prior to discharging other element of conditions. > 15(b) (the remaining part of the condition) requires a Method Statement to be agreed by the LPA prior to that remediation being carried out. > 42(3)and(4) (the remaining part of the condition) - it is not clear if these are considered as needing to be agreed prior to development although 42(3) requires remediation based on the Site Investigation Report which, itself simply recommends certain measures to be observed during groundworks to mitigate impacts of asbestos contamination. 42(4) requires a verification plan which presumably cannot be completed until the remediation works are complete. |  | Submission no. HGY/2022/2615 | 2022-09-06 |  | Response from EHO 11.01.23 - we are satisfied with the partial discharge of ONLY condition 15 (A) on the (site contamination risk assessment and investigation) and 42 (1) and (2) (Additional Contamination - risk assessment and investigation) for the Phase 1 of the approved planning permission HGY/2017/2886.
43 | Phased remediation reporting. Prior to each phase of development being brought into use, a verfication report demonstrating the completion of works set out in the approved remediation strategy and the effectiveness of the remediation shall be submitted to, and approved in writing, by the local planning authority. The report shall include results of sampling and monitoring carried out in accordance with the approved verification plan to demonstrate that the site remediation criteria have been met. | Prior to each phase of development being brought into use
44 | Contamination monitoring and mediation plan. The relevant phase of development hereby approved may not commence (save for demolition) until a monitoring and maintenance plan in respect of contamination for the relevant phase, including a timetable of monitoring and submission of reports to the Local Planning Authority, has been submitted to, and approved in writing by, the Local Planning Authority. Reports as specified in the approved plan, including details of any necessary contingency action arising from the monitoring, shall be submitted to, and approved in writing by, the Local Planning Authority. | Prior to commencement of each phase of development (excluding demolition) | >Partial approval sought (Phase 1 only). >Awaiting response from contamination officer. >Case Officer confirmed in email dated 14.12.22 and 10.01.23 he had sought response from Contamination Officer on condition 44. |  | Submission no. HGY/2022/2615 | 2022-09-06 |  | Email from CO 14.12.22 confirming he will consult EHO re condition 44.
45 | No further development if culvert contamination from construction. Following commencement of the relevant phase hereby approved, contamination not previously identified is found to be present at the site then no further development (unless otherwise agreed in writing with the Local Planning Authority) shall be carried out until a remediation strategy detailing how this contamination will be dealt with has been submitted to and approved in writing by the Local Planning Authority. The remediation strategy shall be implemented as approved. | Remediation strategy required if any previously unidentified contamination is found during construction |  | This condition shall only be triggered should any contamination not previously identified be found on site. In this event a remediation strategy shall be required for approval by the LPA.
46 | No infiltration of surface water drainage unless permitted by LPA. No infiltration of surface water drainage into the ground at this site is permitted other than with the express written consent of the local planning authority, which may be given for those parts of the site where it has been demonstrated that there is no resultant unacceptable risk to controlled waters. The development shall be carried out in accordance with the approved details. | General compliance.
47 | No penetrative construction methods (boreholes, piling etc) unless permitted by LPA. No piling and deep foundation designs, investigation boreholes, ground source heating and cooling systems using penetrative methods shall be carried out on site other than with the written consent of the local planning authority. The development shall be carried out in accordance with the approved details. | Prior to such works being undertaken. | >Partial approval sought (Phase 1 only). >Condition requires approval of details relevant to boreholes / piling before such activities take place (as opposed to purely being prior to commencement of development in general). This query was put to John McRory in email dated 13.12.22. >Condition requires approval of details relevant to boreholes / piling before such activities take place (as opposed to purely being prior to commencement of development in general). >Case Officer chasing Thames Water and Contaminated Land Officer. He confirmed in email dated 23.11.23 that Thames Water were previously consulted. |  | Submission no. HGY/2022/2616 PHASE 1 ONLY | 2022-09-06 | 2023-01-13
48 | Management of boreholes. Prior to the commencement of the relevant phase (save for demolition) hereby approved a scheme for managing any borehole installed for the investigation of soils, groundwater or geotechnical purposes shall be submitted to and approved in writing by the local planning authority. The scheme shall provide details of how redundant boreholes are to be decommissioned and how any boreholes that need to be retained, post-development, for monitoring purposes will be secured, protected and inspected. The scheme as approved shall be implemented prior to the occupation of any part of the permitted development. | Prior to commencement of development (excluding demolition) | Condition requires approval of details relevant to boreholes / piling before such activities take place (as opposed to purely being prior to commencement of development in general). This query was put to John McRory in email dated 13.12.22. BEK confirming relevant details. This effectively says that boreholes (at shallow excavations – max depth of 5m) will not require piling. Such piling would only be required for ‘deeper Cable Percussion’ boreholes to an estimated depth of 20m bgl.
49 | Phasing strategy. This shall be a phased development in accordance with the phasing plan schedule set out in drawing 8688-BOW-A1-01-DR-A-0001-P3 (Proposed Phasing Strategy) unless otherwise agreed in writing by the Local Planning Authority. | General compliance. | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022)
50 | Medical centre. Prior to the commencement of any shell and core fit out of the medical centre full plans detailing the internal layout of the medical centre hereby approved shall be submitted to and approved by the Local Planning Authority. | Prior to commencement of any shell and core fit out of medical centre
51 | CHP Feasibility. Prior to the commencement of above ground works of the relevant phase (save for demolition) hereby approved details of the following will be required to be submitted and approved in writing by the Local Planning Authority: | prior to commencement of above ground works | Wording amended by NMA application HGY/2022/1076 (approved 15/11/2022). Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase.
52 | Fire Statement. (a) No above ground works for each block shall commence, until a detailed Fire Statement for the relevant Block has been submitted to and approved in writing by the Local Planning Authority. (b) The Block shall be thereafter be constructed and managed in accordance with the relevant approved Fire Statement. | prior to commencement of above ground works | Case Officer confirmed in email dated 06.12.22 that condition relates to above ground works of relevant phase.
53 | No permitted change for medical centre. Notwithstanding the provisions of the Town & Country Planning (Use Classes) Order 1987, or any provision equivalent to that Class in any statutory instrument revoking and re-enacting that Order, the premises shall be used as a medical centre (use class E(e)) only and shall not be used for any other purpose including any purpose within Class E(e) or any other use class unless approval is obtained to a variation of this condition through the submission of a planning application. | General compliance.