Transport comments
	Application details


	Date
	28/04/2026

	Planning Reference
	HGY/2026/1170

	Address
	Corner of Scales and Dawlish Road, London, N17 9HN.

	Officer
	

	Description of proposals
	Approval of details reserved by a condition 10 (Demolition Environmental Management Plan) and condition 16 (Method of Construction Statement) attached to planning permission HGY/2022/2000.

	Location Details
	PTAL= 6a, CPZ = The Hale – Monday to Friday: 8.30am-6.30pm, and on event days (Tottenham Hotspur Stadium): Monday-Friday: 8am-8.30pm, Saturday and Sunday: 8am-8pm, public holidays: 12 noon-8pm.  

	Comment:
The details for condition 10 (Demolition Environmental Management Plan) and condition 16 (Method of Construction Statement) will be acceptable for approval and subsequent discharge subject to the following actions being taken:
Condition 10 – Demolition Environmental Management Plan and Condition 16 – Method of Construction Statement
1. S2.5.2 states that there are no schools in the immediate vicinity.  This is incorrect as there is Hyland House School (independent) located off Holcombe Road.  Scheduling of works movements should specifically be scheduled to avoid school pick-up/drop-off times.
2. S3.3.3 Site Set up Activities needs to confirm the following: 
a. An absolute minimum clear footway width of 1.2m is maintained to allow unobstructed pedestrian movement. A wheelchair user/someone with a buggy should be able to continue to be able to use the footway abutting the site. 
b. Access points to the site should open inwards so as not to obstruct pedestrian thoroughfare on the public footway.  
3.  S3.4.1 Foundations – it is stated that concrete lorries will stop adjacent the site on Dawlish Road and Scales Road to pump concrete into the site.  The following clarifications are required:
a. The envisaged length of time and frequency of such activity and resultant number of CPZ parking bays requiring suspension during the activity.   
b. Confirmation is sought that after the concrete pumping is complete, that there will be an inspection of the footway and highway to ensure that no debris is left and if so, it is washed down appropriately.  
4. S4.1.5 Construction Routing Strategy notes that construction vehicle drivers will be required to phone ahead to confirm their delivery slot to ensure that Traffic Marshalls are ready to oversee their safe passage into the temporary loading bay and subsequent transfer of materials to the site.  From this it is unclear as to how early, late and unexpected deliveries will be accommodated and how will it be ensured that there are no instances where there is an excess of deliveries at one time with lorries unable to access the temporary loading bay.  Further details should be provided as to the exact nature of the delivery slot booking mechanism and how this will be managed.   
5. S4.2.7 Parking and Management of Vehicles of Site Personnel states that use of the loading/unloading bay will be permitted for a maximum of 30 minutes.  Clarity is sought as to how this will be enforced.
6. S5.1 Planned Measures Checklist, Table 5.1 Committed, Proposed and Considered Mitigation Measures, has not considered the use of waste compactors to help reduce waste and reduce waste vehicle movements.   
7. S5.3.6 Delivery Scheduling needs to commit to avoiding construction works movements at school drop-off/pick-up times.  This needs to reflect the commitment shown in Table 5.1 to avoid HGV movements during school drop-off/pick-up times. 
8. S5.3.6 states that road sweepers will be utilised as and when required to clear debris from the pavement/highway abutting the site.  The frequency of inspections should be noted.  
9. S5.3.6 states that Just in Time logistics strategy will be employed in relation to materials procurement/deliveries.  Clarity is sought, in the event of supply chain issues, how this would impact upon deliveries.
10. S7.2.2 Mud on public highway needs to state the frequency of inspections to ensure that there is no mud on the highway or footways abutting the site. 
11. S7.2.11 needs to be strengthened to ensure that vehicles carrying dusty loads will be sheeted and fastened securely to prevent any dust or debris from escaping onto footways and the highway abutting the site.  The frequency of checks for any dust/debris spillage should be noted.  
12. S8.2 Waste Reduction needs to outline whether or not waste compactors will be used and if not a justification as to why not. Additionally, any green logistics/reverse logistics measures to be employed should be noted here. 
13.  Figure 4.3 Site Access and Loading/Unloading Areas swept paths, confirmation is sought that whilst the temporary loading bay is occupied by delivery vehicles, that a fire tender would be able to transit safely.  This should be proved by swept path analysis.  
It is not possible to comment specifically on the technical appropriateness of the following in respect of condition 10:
1. Details of any acoustic hoarding; 
2. A temporary drainage strategy and performance specification to control surface water runoff and Pollution Prevention Plan (in accordance with Environment Agency guidance).
3. Details of external lighting.
4. Details of any other standard environmental management and control measures to be implemented.
5. Air Quality and Dust Management Plan.
6. Unexploded Ordnance Survey. 
The above elements of condition 10 are not possible to comment on since they fall outside the remit of the Transport Planning team. Appropriate technical advice should be sought internally as to the suitability of these documents before full approval of details and discharge of the condition.  

In respect of condition 16 – Method of Construction Statement, there are no elements of the condition that can’t be commented on from a transport perspective.  However, it should be noted that clause (f) wheel washing, the applicant has stated that no vehicles will enter/exit the site hence no wheel washing will be required.  It has committed to undertake regular inspections of footways/highway abutting the site and appropriate cleaning to be undertaken.   

	Transport Recommendations:
The details may be approved and subsequent condition discharged from a transport perspective in relation to conditions 10 and 16 once the above-mentioned issues have been addressed. Additionally appropriate internal expert advice should be sought before approving and discharging the condition in areas cited by the Transport Planning team that fall outside their remit.  
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