## Sheet1
37 North Road N6 4BE
Schedule of Essential works of Remediation, Repair and Restoration
The works scheduled below have been executed to arrest further decay to the structure and fabric of the building
| Item |  | Defect | remedial/repair work |  | location |  | reference |  | comment
Interior
Rafters |  | dry rot decayed rafters |  | rafter cut back to sound timber | east, south and west building's |  | H&R Dry Rot survey report |  | severe decay at junction
|  |  |  | 2-300mm and partnered with | perimeter |  | PKS drgs E5 +250506/11 |  | with wall plate, progressive
|  |  |  | matching timber to wall plate |  |  | Mistry Design drg no 2505/6
Wall plates |  | dry rot decayed wall plate |  | Remove wall plate, brick-up in | east, south and part west |  | H&R Dry Rot survey report |  | as above
|  |  |  | matching brickwork | buildings perimeter |  | PKS drgs E5+250506/11
Mistry Design drg no 2505/11
Lintels |  | dry rot decayed lintel |  | Remove lintel [s] replace with | W1,2,4,6,7,8,9 |  | H&R Dry Rot survey report |  | severe decay risk of failure
|  |  |  | RC lintel [s] |  |  | PKS drgs 1-3 + 250506/1,4,7 |  | to lintels referenced,
[7 empty] | Mistry Design drgs no 2505/ |  | progressive
2026-03-01
Joists |  | dry rot decayed joists |  | joist cut back to sound timber | Rooms: G1,2 |  | H&R Dry Rot survey report |  | severe decay at junction with
|  |  |  | 2-500mm and partnered with | F:1,3 |  | PKS drgs E1-4 + 250506/4,7,10 |  | walls on east, south and part
|  |  |  | matching timber to joist | S1 |  | Mistry Design drgs 2505/01-03 |  | west perimeter walls,
|  |  |  | hanger |  |  |  |  | progressive
|  |  |  | Joists cut back 3m [5 no] | F2
|  |  |  | All joists to rear extension | G4/5,F4, roof
Flooring [boarding] |  | dry rot decayed floor boards |  | Remove boards to be replaced | small areas above decayed |  |  |  | not badly damaged, only in
|  |  |  | with matching [reclaimed] | joists |  |  |  | proximity to decayed joists
Flooring [LGF] |  | damp and water penetration |  | New concrete floor, dpm and | LGF |  | H&R Condition survey report |  | extensive damp and water
|  | only 50mm screed no dpm |  | insulation |  |  |  |  | pentration from 35 NR
|  | directly on ground/broken |  | repair drainage to adjoining
|  | brick and stone |  | property
Plaster |  | Infected plaster with dry rot |  | Areas identified removed | Walls: G4/5,F1/2/4 |  | H&R Dry Rot Survey report
PKS Drgs E2-4 + 250506/2-10
|  | Plaster lost due to rafter and |  | Plaster and lathes removed | Ceilings G4/5, G2
joist removal
|  | Water damaged plaster |  | Damaged plaster removed | F2/3,
|  |  |  | Collapsed ceiling areas | S1
Exterior
Architectural features:
Cornice |  | Decayed/collapsed |  | Fully restored by specialist | Front façade |  | H&R Masonry survey report |  | severe decay, features
Pilaster/anthemion |  | Decayed/collapsed |  | masonry contractor |  |  | PKS drgs 250506/12,15 |  | collapsed and progressive
Render |  | failed |  |  |  |  | Mistry Design drg 2505/06
balconette |  | stonework damaged and |  | Fully repaired by specialist
|  | broken in part |  | masonry contractor
Main Roof |  | Defective Spanish slates, |  | New Welsh slates, lead code 5 | Pitched roof |  | H&R Masonry survey report |  | major cause of damage from
|  | all flashings failed |  | flashings and parapet gutter |  |  | PKS drgs 250506/11,12,13 |  | water and dry rot, progressive
Parapet walls |  | Some failed brickwork and |  | Matching brick replacement
|  | pointing |  | repointing in lime mortar
Dormers |  | Totally decayed and failed |  | New timber framework, lead
code 5 dressing