## Sheet1
#VALUE! | Condition | Summary of the Condition | SCALE/FORMAT | Client: Delivered/ Deliverables | Levrant (LVT): Delivered/ Deliverables | OTHER
1 | The works hereby permitted shall be begun not later than 3 years from the date of this consent. | Note
2 | The development hereby permitted shall be carried out in complete accordance with the approved plans and drawings as listed below except where conditions attached to this planning permission indicate otherwise or where alternative details have been subsequently approved following an application for a non-material amendment. Approved plans list: PROPOSED - ROOF January 2025 Block Plan of Site Location Plan Reason: For the avoidance of doubt and in the interests of proper planning. | Note
3 | Pre-Commencement
3.a | A detailed Programme of Works, identifying key stages and milestones. | A detailed Programme of Works, clearly identifying key stages, milestones, and anticipated timeframes for completion, including proposed dates for site visits by required parties. | Excel (.xls / .xlsx) format; clearly structured schedule with dates and milestones. Submitted in a PDF format will be preferable | Client prepared and issued a Programme of Works which was submitted to LVT for review and comment. | LVT reviewed the submitted programme and provided detailed comments and recommendations to ensure sufficient detail, coordination of key stages, and alignment with planning requirements. | Coordination required with Haringey Council regarding proposed inspection dates, where required.
3.b | A full set of existing and proposed drawings (plans, sections, elevations at 1:50 scale) to be prepared with input from Conservation Accredited Architects (RIBA SCA, AABC) including: | A drawing package comprising both ‘as existing’ and ‘as proposed’ sets, including comprehensive annotation and detailed keys identifying repair methodologies. | Plans, sections, and elevations at 1:50 scale; annotated drawings including repair methodology keys. PDF issue for review (CAD if available) | Client produced the drawings and submitted to LVT for review and comment. | LVT reviewed submitted drawings and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| General arrangements | A package of general arrangement drawings to identify the extent of works and areas of intervention. | General arrangements at 1:50 scale; including comprehensive annotation and clearly defined repair methodologies. PDF issue for review (CAD if available) | Client produced the drawings and submitted to LVT for review and comment. | LVT reviewed submitted drawings and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Party wall elevations (No. 37 and No. 39 North Road) | Detailed drawings of the party wall elevations, clearly identifying the existing condition and proposed works. | 1:50 scale; including comprehensive annotation and clearly defined repair methodologies. PDF issue for review | Client included this on the produced drawings and submitted to LVT for review and comment. | This was included on the drawings produced by the client and submitted to LVT. LVT reviewed submitted drawings and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Roof dormers (1:10 scale) | Drawings of the roof dormers, identifying the extent of works and areas of intervention. | To be produced at 1:50 scale; including comprehensive annotation and clearly defined repair methodologies. PDF issue for review | Client produced the drawings and submitted to LVT for review and comment. | LVT reviewed submitted drawings and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Internal plasterwork removal areas | Drawings identifying areas of internal plasterwork removal, clearly defining the extent of removal and areas of intervention and the extent of removal, including areas already undertaken and those proposed. | To be produced at 1:50 scale; including comprehensive annotation and clearly defined repair methodologies. PDF issue for review | Client included this information on the produced drawings and submitted to LVT for review and comment. | LVT reviewed submitted drawings, as well as additional information provided by the reports undertaken, and provided comments, advice and recommendations. This was repeated where necessary.
| Timber repairs and floorboard lifting areas | Drawings identifying areas of timber repair and floorboard lifting, including both ‘as existing’ and ‘as proposed’ information. | To be produced at 1:50 scale; including comprehensive annotation and clearly defined repair methodologies. PDF issue for review | Client included this information on the produced drawings and submitted to LVT for review and comment. | LVT reviewed submitted drawings, as well as additional information provided by the reports undertaken, and provided comments, advice and recommendations. This was repeated where necessary.
| Detailed drawings illustrating methodology and interface of internal structural and timber repairs at junctions with the existing historic fabric |  | Scales 1:10, 1:5, or 1:2 as appropriate | Client included this information on the produced drawings and submitted to LVT for review and comment. | LVT reviewed submitted drawings, as well as additional information provided by the reports undertaken, and provided comments, advice and recommendations. This was repeated where necessary.
3.c | Final Heritage Method Statements consolidating previous submissions and detailing all proposed interventions. | The consolidation of previous submissions that clearly sets out all proposed interventions to the historic fabric of the building, the conservation-led methodology, materials to be used, and methods of protection. This should be cross-referenced with all drawings. | .doc, .pdf | Client prepared a final document consolidating all previous submissions, including reports and drawings, for submission directly to Haringey Council. | As this document was an amalgamation of all precious material, it was sent directly to Haringey Council as part of the final submission package. Previous Heritage Statements composed by Hutton and Rostron were read by LVT prior to submission.
3.d | Material specifications and samples for: | A record documenting both the materials already used and those proposed for upcoming works. For works already completed, confirmation of the exact materials supported by appropriate evidence and verification. | .Word document (.doc / .docx), supported by material samples where required. Include photographs and product information / datasheets where available/ required. | Client prepared and submitted a materials schedule, including specifications and samples (where required) | LVT reviewed submitted documentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Replacement bricks | Confirmation of the replacement bricks used in completed works, including specification, source, and compatibility with the existing historic fabric. | .Word document (.doc / .docx), supported by material samples where required. Include photographs and product information / datasheets where available/ required. | Client prepared and submitted a materials schedule, including specifications and samples (where required) | LVT reviewed submitteddocumentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Repointing mortar | Confirmation of repointing mortar used, including mix proportions, constituent materials, appearance (colour and texture), and method of application. | .Word document (.doc / .docx), supported by material samples photographs and product information / datasheets where available/ required. | Client prepared and submitted a materials schedule, including specifications and samples (where required) | LVT reviewed submitteddocumentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Render | Confirmation of the render specification used in completed works and proposed for future works. | .Word document (.doc / .docx), supported by material samples photographs and product information / datasheets where available/ required. | Client prepared and submitted a materials schedule, including specifications and samples (where required) | LVT reviewed submitteddocumentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Slates | Details of the roof slates used in completed works and proposed for future works. | .Word document (.doc / .docx), supported by material samples photographs and product information / datasheets where available/ required. | Client prepared and submitted a materials schedule, including specifications and samples (where required) | LVT reviewed submitteddocumentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
| Rainwater goods | Information to be provided on retained/reused rainwater goods. | .Word document (.doc / .docx), supported by material samples photographs and product information / datasheets where available/ required. | Client prepared and submitted a materials schedule, including specifications and samples (where required) | LVT reviewed submitteddocumentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
3.e | Moulding profiles (internal and external) to be recorded and submitted | Record of internal and external moulding profiles, capturing the form and detail of existing historic fabric. | Typically 1:10, 1:5, or 1:2 scale, with reference to corresponding 1:50 general arrangement drawings. | Client prepared and submitted drawings of ceiling cornice, skirting and picture rail, and submitted to LVT for comment. | LVT reviewed submitted drawings and provided comments, advice and recommendations for improvement. This was repeated where necessary.
3.f | A strategy for targeted removal of wall and ceiling plaster, limited to one metre beyond visibly decayed areas, to be agreed with the LPA and HE. | A detailed method statement for the targeted removal of plaster, covering both works already undertaken and those proposed, demonstrating a conservation-led approach, minimising loss of historic fabric. | Report (.doc/.pdf) supported by annotated drawings identifying areas of plaster removal; PDF issue for review. | This information was provided in the reports by Hutton and Rostron, as well as within the drawings prepared by the client and the proposed schedule. It was composed by the client and submitted to LVT for comment. | LVT reviewed submitteddocumentation and provided comments, advice and recommendations for improvement. This was repeated where necessary.
3.g | Confirmation that all works will be overseen by a Conservation Accredited Architect (RIBA SCA or AABC) | Confirmation of LVT's formal appointment to be provided to Haringey Council. | Written confirmation (.doc/.pdf), supported by appointment details where appropriate. | Client provided written confirmation of LVT appointment directly to Haringey Council. | LVT formally confirmed their appointment and provided commentary on what has been undertaken and what is proposed to the relevant Conservation Officer and associated colleagues. | The extent of conservation oversight is not clearly defined and as this relies upon a third party, we have doubts that it complies with the “Six Tests” of validity for imposing conditions. and will therefore be interpreted as deemed appropriate and reasonable
4 | Monitoring and notification during works: Throughout the duration of the works, a robust programme of monitoring, documentation, and communication shall be maintained to ensure transparency, safeguard the historic fabric, and enable timely oversight by LPA and HE. The following measures shall be implemented: | A structured process for monitoring, recording, and reporting throughout the works, detailing methodology where required. | Written monitoring strategy (.doc/.pdf), supported by records including photographs, site notes, and meeting minutes where appropriate. | Client has implemented and maintained a monitoring and reporting process, including preparation of records documenting progress, site conditions, and key stages of the works. Records to be made available to LVT, the LPA, and Historic England as required. | LVT attended/to attend site meetings, review progress, and provide advice, maintaining records of inspections and key discussions where appropriate.
4.a | Moisture readings and visual inspections shall be undertaken and recorded at each key stage | Moisture readings and visual inspections carried out at each key stage using appropriate equipment and methodologies. | Submitted as .xcl, .pdf or .doc. | Client has undertaken moisture monitoring and visual inspections, and is to maintain this process throughout all stages . To be shared with LVT at each key stage. | LVT reviewed submitted inspection records, keeping a copy of the readings on file. LVT to ask for updates to the readings going forward. | Records should be made available to the LPA and Historic England upon request.
4.b | The LPA shall be notified prior to the commencement of each key stage | The client will notify the Local Planning Authority in advance of each key stage of the works, to enable appropriate oversight and coordination. |  | Going forward, the client is to notify the LPA in advance of each key stage, following recommendation and advice from LVT. | LVT will advise on the opriate timing of notifications and key stages requiring LPA involvement where needed.
4.c | A site meeting with the Conservation Officer shall be arranged at each key stage to review progress and building condition | The client will arrange site meetings at each key stage with the Conservation Officer to review progress and assess the condition of the building. The purpose of these meetings is to facilitate the review of works affecting the historic fabric and to agree on any necessary actions. | Meeting records to be maintained (.doc/.pdf), including minutes and photographic documentation where appropriate. | Client to arrange and coordinate site meetings with the Conservation Officer at each key stage, and ensure that records of discussions and agreed actions are maintained. | LVT to attend site meetings with the Conservation Office, provide advice, and record key discussions and recommendations where appropriate.
4.d | All works shall be recorded, and records submitted for approval at the end of each key stage. | The client is to maintain a comprehensive record of all works undertaken at each key stage, including progress, interventions, and any changes to the agreed scope. The record should include sufficient detail to demonstrate compliance with the approved drawings, specifications, and method statements. | Recorded information (.doc/.pdf), including photographic records, site notes, and supporting documentation where appropriate. | Client to continue preparing and submitting a comprehensive record of works at the end of each key stage, including photographic evidence and supporting documentation, for review. | LVT reviewed records and provided comments and recommendations, confirming whether the works are in accordance with approved details. To continue providing advise and recommendations as the project progresses.
5 | Execution of works: All works shall be undertaken in strict accordance with the approved details, drawings, and Method Statements submitted under Sections A and B. The following principles shall apply throughout the execution phase to ensure the protection and sensitive treatment of historic fabric: | The client will ensure that all works are carried out in accordance with the approved drawings, specifications, and Method Statements. | N/A – applies to all works on site; supported by approved drawings and Method Statements. | Client to ensure works are carried out in accordance with approved details and to notify LVT of any proposed changes or unforeseen issues. | LVT to monitor/monitoring works through site visits and provide advice to ensure compliance with approved details and conservation best practice.
5.a | Investigatory and remedial works shall be carried out with minimal loss of historic fabric. | Client to ensure that investigatory and remedial works shall be carried out with minimal loss of historic fabric. |  | Client to ensure that all works are carried out in accordance with conservation principles and approved details, minimising loss of historic fabric. | LVT to continue to provide advice on conservation best practice and recommend appropriate methods to minimise impact on historic fabric.
5.b | Internal plasterwork shall be renewed to match existing finishes. | Client is to ensure that any renewal of internal plasterwork accurately matches the existing finishes in terms of material, texture, profile, and appearance. |  | Client to ensure that all internal plasterwork repairs and renewals are carried out in accordance with approved details, matching existing finishes. | LVT to continue to provide advice on conservation best practice and recommend appropriate methods to minimise impact on historic fabric.
5.c | Embedded timbers shall be carefully removed and replaced with brick-and-mortar infill. | Client to ensure that the removal of embedded timbers and associated infill works are carried out in accordance with approved details and conservation principles. |  | To ensure that the removal of embedded timbers and associated infill works are carried out in accordance with approved details and conservation principles. | LVT to continue to provide advice on conservation best practice and recommend appropriate methods to minimise impact on historic fabric.
5.d | Historic rainwater goods shall be retained and repaired where possible. | Historic rainwater goods are retained and repaired where possible, and replacement limited to instances where repair is not feasible. |  | Client has ensured that rainwater goods are retained and repaired where possible, with any replacements carried out in accordance with approved details. | LVT to continue to provide advice on conservation best practice and recommend appropriate methods to minimise impact on historic fabric.
5.e | Slates posing safety risks shall be removed and set aside for selective re-use. | Where slates have been removed or replaced, the client is to provide details of the works undertaken, including extent, specification, and rationale. Any further works should ensure that slates are retained and reused where possible, with replacement limited to where necessary for safety or condition reasons. | Specification document (.doc/.pdf), supported by photographic record and product information. | Client provided details of the slates that were removed, replaced, or retained, including supporting photographs, the extent of the works, and relevant specifications or product information. | LVT reviewed the submitted information and provided commentary, where necessary, on work carried out, suitability and compliance.