Transport comments
	Application details


	Date
	13/08/2026

	Planning Reference
	HGY/2026/2153

	Address
	85, High Road, Wood Green, London, N22 6BB.

	Officer
	

	Description of proposals
	Approval of details reserved by a condition 4 (Construction Management Plan) attached to planning reference HGY/2024/1785.

	Location Details
	PTAL= 6b, CPZ = Wood Green Outer Zone – Monday to Saturday 8am to 6:30pm.  

	Comment:
The details will only be acceptable for approval and subsequent discharge of condition 4 – Construction Management Plan once the following issues have been addressed:
1. S3.2 needs to provide a summary table of construction vehicle movements by type and phase of works.
2. S3.3 states that the main access route to the site for deliveries/works movements will be via Amber Mews off Brampton Park Road. Confirmation is sought that all vehicles requiring access will be able to do so, given the relatively narrow width of the road.  
3. S3.5 needs to outline how early, late and unexpected works deliveries will be managed.  
4. S3.9 needs to be strengthened to commit to works movements/deliveries avoiding high peak hours (08:00-09:00 and 17:00-18:00) and avoid school drop-off and pick-up times (08:00-09:00 and 17:00-18:00).  
5. Similar to S3.9, S4.7 needs to commit to no deliveries at high peak hours (08:00-09:00 and 17:00-18:00) and no movements at school pick-up and drop-off times (08:00-09:00 and 15:00-16:00).  
6. S4.10, Table 1, Approximate Development Schedule needs to be updated to reflect new timescales.  
7. S4.13 needs to specify the frequency of inspections and cleaning of footways and highways for dust and spoil resulting from the construction works.  It also needs to specifically commit to ensuring that works movements are sheeted and fully secured to ensure no discharge of dust or spoil onto footways and the highway. 
8.  The applicant needs to outline any parking bay suspensions required to accommodate skips etc on Brampton Park Road, giving details of the number of bays requiring suspension and length of suspension.  
9. The applicant needs to commit to ensuring that any hoarding, has doorways that open inwards so as not to impede on pedestrian thoroughfare.  
10. The applicant needs to outline what green/reverse logistics measures will be employed.

	Transport Recommendations:
The approval of details for condition 4 Construction Management Plan will only be acceptable and for subsequent discharge of the condition, once the above-mentioned issues have been addressed.     
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