## Programme_of_Works_84_Highgate_
PROGRAMME OF WORKS
84 HIGHGATE HIGH STREET, N6 5HX (2026)
WBS | Task Description | Start Date | Completion Date | Duration (Days) |  | W1 5/10/26 | W2 12/10 |  | W3 19/10 | W4 26/10 | W5 02/11 | W6 09/11 | W7 16/11 | W8 23/11 | W9 30/11 | W10 07/12 | W11 14/12 | W12 21/12 | W13 11/1/27 | W14 18/1/27 | W15 25/1/27
GROUND FLOOR - GALLERY
1.1 | Start on Site. Initial walkthrough with conservation officer |  | 2026-10-05 | 1 | X
| Task 1.2 to Ground Floor related to Masonry & Cleaning: Brickwork Repairs, Paint Removal & Repointing |  |  |  | X
| CO to inspect before full-scale work During a sample trial panel for paint cleaning and |  |  |  | X
| mortar specification |  |  |  | X
1.2 | Repairs to exposed brickwall and brick cleaning, repointing |  |  | 10
1.3 | First Fix Wiring with sockets placed in skirting box to brick wall |  |  | 10
| Tasks 1.3 to Ground Floor and 2.3 to Basement related to Masonry & Cleaning: Brickwork Repairs, | [6 empty] | X
| Paint Removal & Repointing CO to Inspect immediately after First Fix routing, before walls/ | [6 empty] | X
| chases are closed or plasterboard/skirtings are fitted.chases are closed or plasterboard/ | [6 empty] | X
| skirtings are fitted. | [6 empty] | X
| CO to Inspect BEFORE plastering or dot-and-dab installation starts. |  | 2026-10-19 | 1 |  |  |  | x
1.4 | Plastering Works |  |  | 10
| Task 1.5 to Ground Floor related to Historic Roof Structure & Glazing Replacement: Glass Roof & |  |  | 1 | X
| Flashings, CO to Inspect once the old glazing is stripped back, before installing new double-glazed |  |  |  | X
| units and flashings. |  | 2026-10-05 |  | X
1.5 | Fit Glass Roof |  |  | 10 | X
| CO to Inspect when existing floors are lifted, before laying subbases and Amtico/carpet overlay. |  |  |  | x
1.6 | 2nd Fix Joinery, Electrics, Floor Finishes & Tiling |  |  | 15
1.7 | Decoration & Final Fixtures Installation |  |  | 20
BASEMENT - GALLERY
2.1 | Start on Site. Initial walkthrough with conservation officer |  | 2026-10-05 | 1 | X
2.2 | Fit Stairs & Studwork |  |  | 20
2.3 | First Fix Wiring |  |  | 20
2.4 | CO to Inspect BEFORE plastering or dot-and-dab installation starts. |  | 2026-10-05 | 1 | X
2.5 | Plastering Works |  |  | 15
| CO to Inspect when existing floors are lifted, before laying subbases and Amtico/carpet overlay. |  |  |  | x
2.6 | 2nd Fix Joinery, Electrics, Floor Finishes & Tiling |  |  | 20
2.7 | Decoration & Final Fixtures Installation |  |  | 3
FIRST AND SECOND FLOOR WORKS - RESIDENTIAL
3.1 | Start on Site. Initial walkthrough with conservation officer |  | 2026-10-05 | 1 | X
| CO to Inspect BEFORE plastering or dot-and-dab installation starts. |  |  |  | X
3.2 | Plastering Works |  |  | 20
| CO to Inspect when existing floors are lifted, before laying subbases and Amtico/carpet overlay. |  |  |  | X
3.3 | 2nd Fix Joinery, Electrics & Tiling |  |  | 35
3.4 | Decoration, Sanitary Ware, Floor Finishes, Kitchen & Electrics |  |  | 25
SPECIFICATION OF WORK
GROUND | BRICKWORK REPAIRS | Remove any damaged, cut bricks, clean paint from bricks using non abrasive methods and repoint with Lime motar
| FIRST FIX WIRRING TO GROUND FLOOR | Instal electrics as approved on drawings, including all sockets on exposed brickwall to be fixed to extended skirting to avoid damage of brickwork
| PLASTERING WORKS TO GROUND FLOOR | Skim coat to existing plaster surfaces and new walls and ceilings
| NEW GLASS ROOF TO GROUND FLOOR | Remove damaged single wired glazed roof and replace with double glazed units ontop of existing timber supports, reuse existing lead flashing where possible and replace to match existing as needed.
| SECOND FIX ELECTRICS, FLOOR FINISHES , SKIRTINGS | Painted sockets to match wall colour. Fit Amtico floor to existing subbase, ogee Architraves and skirtings as detailed
| DECORATION AND FINAL FIXTURE INSTALLATION | Paint all plaster and timber surfaces and installation of glass screens as detailed
BASEMENT | FIT STAIRS AND STUDWORK | Fit new stair to basement to match those of upper floor with simple timber balusters, Fit
| FIRST FIX WIRRING | Install first fix electrics to avoid any chasing of wall or floor
| PLASTERING WORKS TO BASEMENT | Install plasterboard on dabs to avoid any penetration of damp proofed walls and to hide wirring. Skim coat to walls and ceiling
| SECOND FIX ELECTRICS, FLOOR FINISHES AND TILING | Painted sockets to match wall colour. Fit Amtico floor to existing subbase, ogee Architraves and skirtings as detailed
| DECORATION AND FINAL FIXTURE INSTALLATION | Paint all plaster and timber surfaces and installation of glass screens as detailed
FIRST & | PLASTERING WORKS TO GROUND FLOOR | Skim coat to existing plaster surfaces and new walls and ceilings
SECOND | 2ND FIX JOINERY, ELECTRICS AND TILING | Install second fix electrics as agreed plan . Fit Ogee architraves and skirtings and ceramic tiling to bathroom. Fit handrail to staircase balustrade as approved details and glass panels as approved details
FLOORS | DECORATION, SANITARY WARE, FLOOR FINISHES, KITCHEN | Install Amtico over existing sub base to upper floor and carpet to first floor. Install sanitary ware and decorate all plaster and timber surfaces
Summary purpose of site inspections:
· Task 1.2 - Brick Cleaning & Repointing: inspect Sample trial panel & mid-works to ensure non-abrasive cleaning & correct lime mortar mix
· Tasks 1.3 / 2.3 - First Fix Electrics: inspect post-first fix, pre-plastering to confirm zero masonry chasing & skirting socket mounting
· Task 1.5 - Glass Roof Replacement: inspect post-strip out, pre-glazing to assess historic timber support condition & lead flashing details
· Tasks 1.4 / 2.5 / 3.2- Substrates & Plastering: inspect pre-plastering substrate to check breathability, damp management, and original plaster retention where it survives
· Tasks 1.7 / 2.6/ 3.5 - Floor Subbase & Timber Floorboard Protection: inspect floors to check floorboards preservation, where these survive