## Sheet1
Wood Green, Stuart Crescent N22 - Redevelopment of Former Social Club to include new build houses, refurbisments, and conversion works to existing structures
| WK1 - WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41
Week Commencing Monday 1st May 2023
Contract lead in time
Aesbestos Surveys and Removal
Preliminaries and Health and Safety Reviews
Site Set Up | bar: WK7 to WK9
Enabling Works and Demo | bar: WK8 to WK11
Drainage & Foul Connection | bar: WK10 to WK18; WK38 to WK40
Rain water Drainage & Soakaways | bar: WK14 to WK19; WK38 to WK40
Service Duct Works | bar: WK15 to WK19; WK39 to WK41
Excavation & Foundation Buildings | bar: WK10 to WK13
Foundation Masonry Buildings | bar: WK15 to WK19
Block & Beam Grnd-Fl Buildings | bar: WK17 to WK18
Concrete Oversite | bar: WK18 to WK20
Block & Beam | bar: WK19 to WK20
Masonry Ground To 1st Floor | bar: WK18 to WK25
Scaffolding | bar: WK19 to WK39
Structural Steel Works | bar: WK22 to WK26
Block & Beam / Plank 1st Floor | bar: WK25 to WK29
Masonry 1st Floor to Uppers | bar: WK25 to WK32
Roof Carpentry | bar: WK26 to WK36
Roof Houses | bar: WK31 to WK38
Rain Water Goods | bar: WK36 to WK39
Window installation | bar: WK33 to WK40
Finals and Snagging | bar: WK38 to WK41